## Sheet1
ID | Work Item Type | Title 1
205000 | Epic | Milestone 1 – Assess and Review
205001 | Feature | During this phase partner will work with customer to assess the environment readiness.
205002 | User story | · Identify and document contacts for this project
205003 | User story | · Present Windows Virtual Desktop: Prerequisites and requirements
205004 | Task | o Review supported Operation Systems and licensing requirements
205005 | Task | § Confirm Operating Systems to deploy
205006 | Task | § Confirm licensing requirements have been met
205007 | Task | o Review Azure Active Directory requirements
205008 | Task | § Confirm requirements have been met
205009 | Task | o Review, document in-scope Users and their Application requirements
205010 | Task | § Microsoft applications
205011 | Task | § Third party commercial applications
205012 | Task | § Custom applications
205013 | Task | § Confirm in-scope application(s) that require GPU acceleration
205014 | Task | o Review and confirm OS images to deploy
205015 | Task | § Marketplace images
205016 | Task | § Custom images
205017 | Task | o Review, document Windows Virtual Desktop session hosts and host pool requirements based on User count and application requirements
205018 | User story | · Present FSLogix: Prerequisites and requirements
205020 | User story | · Present SMB File Share: Prerequisites and requirements
205021 | Task | o Extend to Azure vs. Connect to on-premises
205029 | Epic | Milestone 2 – Validation
205030 | Feature | During this phase partner will work with customer to Validate the environment readiness.
205031 | User story | · Validate pre-requirements have been completed
205032 | User story | · Create and configure host pools and session hosts
205033 | User story | · Validate Windows Virtual Desktop deployment
205038 | Epic | Milestone 3 – Readiness - Setup landing zone
205039 | Feature | These items are addressed as needed and might have impact to timeline. These items will be addressed as mutually agreed by customer and partner.
205040 | User story | · Create Azure Tenant
205041 | User story | · Azure Virtual Network
205042 | User story | · Azure Bastion
205043 | Task | o Create Azure Bastion host for target subscriptions
205044 | Task | § Services, Prod, PreProd, Users, Storage
205045 | User story | · Hybrid Cloud Connectivity (HCC)
205046 | Task | o Azure VPN Gateway (Site-to-Site VPN)
205047 | Task | § Configure S2S VPN between Azure and on-premises network / firewall
205048 | User story | · Resilient Identity Pattern (RIP)
205049 | Task | o Extend on-premises AD Forest to Azure
205050 | Task | § Create 2x Domain Controllers in Azure (one in each geo redundant datacenter region)
205051 | Task | § Add to on-premises forest
205052 | User story | · Azure AD Sync
205053 | Task | o Create Azure AD Sync VM in MAC
205054 | User story | · Cyber Security & Monitoring (SIEM/SOAR)
205055 | Task | o Azure Sentinel
205056 | Task | § Setup Sentinel
205057 | Task | § Configure Syslog Linux VM
205058 | Task | § Configure Firewalls to ship Syslog’s to Linux VM
205059 | User story | o Azure Security Center
205060 | Task | § Create ASC tenant
205061 | Task | § Add ASC Standard to resilient identity VMs (DC's, AAD Sync) across all subscriptions and services
205062 | Task | § Add connectors
205063 | User story | · Backup & Recovery (BUR)
205064 | Task | o Azure Backup
205065 | User story | · Business Continuity & Disaster Recovery (BCDR)
205066 | Task | o Azure Site Recovery
205067 | User story | · Resilient File Servers (RFS)
205068 | Task | o Azure Files ¦ Azure File Sync
205069 | User story | · Windows Virtual Desktop (WVD)
205070 | Task | o Domain Prep
205071 | Task | § Create different OU's for each host pool type (app and desktop) in a child OU of the VDI OU:
205072 | Task | § Parent machine OU = “WVD”
205073 | Task | § Child machine OU = “WVD APP”
205074 | Task | § Child machine OU = “WVD Desktop”
205075 | Task | · Create User Groups for planned host pools
205078 | Epic | Milestone 4 – Windows 10 Image Customization and Deployment
205079 | Feature | During this phase vendor will work with customer deploy customized Session Host images for use in the Windows Virtual Desktop environment as defined in Milestone 1 documentation.
205080 | User story | · Create custom images as defined in Milestone 1
205081 | Task | · Validate custom images
205082 | Task | · Deploy custom imaged to Windows Virtual Desktop environment
205087 | Epic | Milestone 5 - Deploy and Configure FSLogix
205088 | Feature | During this phase vendor will work with customer to deploy FSLogix to the Windows Virtual Desktop environment. Tasks include
205089 | Task | · Validate pre-requirements have been completed
205090 | Task | · Deploy and Configure FSLogix container
205091 | Task | · Confirm agent FSLogix is installed
205097 | Epic | Milestone 6 – Fileshares Design, Strategy and Deployment
205098 | Feature | During this phase vendor will work with customer to extend Customer’s SMB file shares to Azure or connect the Windows Virtual Desktop environment to on-premises infrastructure. Tasks include
205099 | Task | · Strategy: Extend vs. Connect
205100 | Task | · Review: Design prerequisites for each option
205101 | Task | · Deploy: Extend or Connect
205102 | Task | · Validate access to SMB shares